## Sheet1
Project Master
Task | Summary | Details @ | Team | Reporter | Due
Read Chapter 14 of Rocket Propulsion Elements | - | - | all | all | 2016-06-27
Manufacturing Practice | Determine materials necessary for manufacturing practice and resulting products |  | Manufacturing | Richard, Kenny | 2016-07-09
Motor Calc Sheet Validation | Verify the formulas and methods used in the motor calculation sheet | /Launches/8-inch/design/calculations/trunk/ | Design, Analysis | Neal | 7/11/2016
Motor Calculations | Validate motor calculations for Q-motor | - | Design | William | 2016-07-15
CAD Entire Rocket | *work with SLV | - | Design |  | 2015-07-15
Generate BOM for Nozzle |  | - | Manufacturing | Kenny | 2015-07-11
Finish CAD for Nozzle |  | /Launches/8-inch/design/CAD/trunk | Design | Bill | 2015-07-15
Quote from John/Order Grains |  | - | Manufacturing | Richard | 2015-07-15
CAD Forward Bulkhead |  | - | Design | Neal | 2015-07-22
* we need 4 weeks lead time to get grains cast